## Sheet1
Story ID | Story Name | Description | Priority | Iteration (Sprint) number | Acceptance Criteria | Estimation | Notes | Date started (or planned) | Date finished (or planned)
|  | This is an example. As a <> I want <> So that <> |  |  | This is an example. This is a new line 1. List 1 2. List 2 3. List 3
1 |  | As a TA, I want to create an account so that I can apply for jobs | High | Sprint1 | Account can be created
2 |  | As a TA, I want to upload CV | high | Sprint1 | CV file uploaded successfully