## Product Backlog
Story ID | Story Name | Description | Priority | Iteration (Sprint) number | Acceptance Criteria | Estimation | Notes | Date started (or planned) | Date finished (or planned)
1 | TA Account Registration | As a TA Applicant, I want to register an account, So that I can apply for TA positions | High | Sprint1 | 1. System validates unique student ID/email 2. Password meets complexity (8+ chars, letters+numbers) 3. Data saved to JSON file 4. Success/failure feedback displayed | 8 | Unified JSON storage, input validation required ¦ TECH NOTE: Ensure 'unique check + write' as atomic operation under lock to prevent race conditions
2 | TA Login Function | As a TA Applicant, I want to log in to the system, So that I can access my application dashboard | High | Sprint1 | 1. Validate username/password against JSON data 2. Clear error for invalid credentials 3. In-memory session maintenance 4. Logout clears session 5. Role-based menu loading | 6 | Role identification on login, session management
3 | TA View Positions | As a TA Applicant, I want to view available TA positions, So that I can choose which to apply for | High | Sprint1 | 1. Display position title, module, requirements, deadline, vacancy 2. Data pulled from JSON file 3. Sort by deadline/module name 4. Graceful empty state handling 5. File read lock to prevent conflicts | 7 | Basic sorting function, file locking mechanism
4 | TA Submit Application | As a TA Applicant, I want to submit applications, So that I can apply for desired positions | High | Sprint2 | 1. Form captures personal info, skills, availability 2. Check deadline and vacancy before submission 3. Save to JSON linked to position ID 4. Confirmation message 5. File write lock with sync mechanism 6. Store uploaded CV in /uploads/cv with unique filename (studentID_timestamp.ext), record file path in JSON | 9 | Vacancy check critical, data consistency guarantee; Add CV file I/O with error handling (disk space/permission check); upload+path recording+submission as atomic operation under lock; validate file size/format (PDF/Word, ≤5MB)
5 | MO Login Function | As a Module Organizer (MO), I want to log in, So that I can manage TA positions | High | Sprint1 | 1. Separate MO dashboard 2. Auth against MO-specific JSON data 3. Role-based access control on login 4. In-memory session maintenance | 5 | MO-specific permission initialization
6 | MO Create Position | As a MO, I want to create position postings, So that applicants can apply | High | Sprint2 | 1. Form captures title, module, requirements, deadline, workload, vacancy 2. Save to JSON with unique ID 3. Preview before publishing 4. Required fields validation 5. File write lock 6. Own positions only displayed | 8 | Permission control integrated, unique ID generation ¦ TECH NOTE: Ensure 'unique ID generation + write' as atomic operation under lock to prevent duplicates
7 | MO View Applications | As a MO, I want to view applications for my positions, So that I can review candidates | Medium | Sprint2 | 1. View only own positions' applications 2. Display applicant info, submission date, status 3. Filter by status (pending/reviewed) 4. File read lock | 7 | Permission filter critical, status filtering
8 | MO Approve/Reject Apps | As a MO, I want to mark applications as approved/rejected, So that candidates get feedback | Medium | Sprint3 | 1. Update status in JSON file 2. Record status change timestamp 3. Confirmation prompt to prevent mistakes 4. File write lock 5. Trigger offer notification for approval | 6 | Status tracking, notification mechanism
9 | Admin Login Function | As an Admin, I want to log in, So that I can manage overall system data | High | Sprint1 | 1. Highest access level role 2. Separate admin dashboard 3. Auth against admin JSON data 4. In-memory session maintenance | 4 | Admin-specific permissions, secure login
10 | Admin Manage MO Accounts | As an Admin, I want to manage MO accounts, So that I can add/remove MO access | Medium | Sprint3 | 1. Create/edit/delete MO accounts in JSON 2. Log all changes to text file 3. Prevent deletion of MO with active positions 4. File write lock | 7 | Change logging required, active position check
11 | Admin View Workload Data | As an Admin, I want to view TA workload data, So that I can balance assignments | Medium | Sprint3 | 1. Aggregate workload from JSON data 2. Display summary stats (total hours, avg per module) 3. Export to JSON/CSV 4. File read lock | 8 | Data aggregation, export function
12 | Admin Generate Reports | As an Admin, I want to generate recruitment reports, So that I can track progress | Low | Sprint4 | 1. Report shows positions, apps, approvals, accepted offers 2. Save as text/JSON 3. Time period/module filter 4. File read lock | 9 | Report filtering, multiple formats support
13 | TA View Application Status | As a TA Applicant, I want to view my application status, So that I know if approved | Medium | Sprint3 | 1. View all own submissions (pending/rejected/approved/offer) 2. Real-time status updates 3. Clear labels and offer prompts 4. File read lock | 5 | Status visualization, real-time sync
14 | Password Reset Function | As a User (All Roles), I want to reset password, So that I can recover access if forgotten | Low | Sprint4 | 1. Reset via student ID + security question 2. Save new password to JSON (meets complexity) 3. Log to text file (simulate email) 4. Success/failure feedback 5. File write lock | 8 | Security question verification, simulation of email
15 | Admin AI Workload Balance | As an Admin, I want basic rule-based logic for workload balance, So that TA assignments are fair | Low | Sprint4 (Optional) | 1. Rule-based if-else logic (no external ML) 2. Analyze workload & app data from JSON 3. Suggest adjustments for overloaded TAs 4. Display as text report 5. File read lock | 12 | Optional feature, simple statistical analysis only
16 | TA Withdraw Application | As a TA Applicant, I want to withdraw applications, So that I can correct errors or abandon | Medium | Sprint3 | 1. Withdraw only own pending/approved (unaccepted) apps 2. Confirmation prompt 3. Update status to 'withdrawn' in JSON 4. Success feedback 5. File write lock 6. Restore vacancy if applicable | 5 | Vacancy restoration, status tracking
17 | MO Modify/Delete Positions | As a MO, I want to modify/delete my positions, So that I can adjust info or cancel | Medium | Sprint3 | 1. Modify/delete only own positions 2. Warning for deleting positions with apps 3. Update with timestamp for modification 4. Mark as invalid (not remove) for deletion 5. File write lock 6. Sync vacancy updates | 7 | Data traceability, vacancy sync
18 | Admin Clean Invalid Data | As an Admin, I want to delete invalid data, So that I can clean up redundancy | Medium | Sprint4 | 1. Mark invalid positions/apps as deleted in JSON 2. Log deletion (who, when, reason) 3. Confirmation prompt 4. Sync associated data (restore vacancy) 5. File write lock | 6 | Data cleaning, audit trail
19 | MO Permission Isolation | As a MO, I want system to restrict viewing other MOs' data, So that data privacy is ensured | Medium | Sprint2 | 1. Permission control on all data access 2. Cannot access other MOs' positions/apps 3. Insufficient permission prompt 4. Log access violations 5. Stable permission logic | 4 | Critical for data security, violation logging
20 | TA Data Privacy Protection | As a TA Applicant, I want system to restrict viewing other TAs' data, So that privacy is protected | Medium | Sprint2 | 1. Permission control on application data 2. Cannot access other TAs' info/status 3. Insufficient permission prompt 4. Log access violations 5. Display only own data | 4 | Privacy compliance, data isolation
21 | Admin Role Permission Control | As an Admin, I want clear role permission distinction, So that unauthorized operations are prevented | High | Sprint2 | 1. RBAC applied to all functions/data 2. Admin: view all, modify system; MO: own data; TA: own account 3. Block and log unauthorized operations 4. Clear permission prompts 5. Sync RBAC with all operations | 6 | Core security feature, comprehensive RBAC
22 | TA Accept/Reject Offer | As a TA Applicant, I want to accept/reject approved offers, So that position status is updated | High | Sprint3 | 1. Only for 'approved' status applications 2. Confirmation prompt 3. Accept: update to 'accepted', reduce vacancy 4. Reject: update to 'rejected', restore vacancy 5. Real-time sync to MO dashboard 6. File write lock 7. Record timestamp | 5 | Critical for workflow closure, vacancy management